## Specification
Project: | Xcidic Assessments
Version: | 1.0.0
Date: | 2021-08-15
SYSTEMS
Specifications | Types | Versions
Nodejs | Core | 12.22.5
Postgresql | Core | 8.7.1
Reactjs | Core | 17.0.2
Express | subsystems | 4.17.1
Nodemon | subsystems | 2.0.12
SERVER
Specifications | Types | Versions
Guides
1) gitpull: https://github.com/revandahadwiansyah/public_assessments.git
2) cd fatbellies
2.1) npm install
2.2) ./run.sh
3) cd node-react
3.1) npm install
3.2) npm start

## Gantt Chart
Project | Xcidic Assessment
Date | 2021-08-16
Time Schedules | 16 Aug - 22 Aug 2021
Phase | Task Name | 2021-08-01
|  | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | 1. Documentation
1.1 Requirement Analyst
1.1.1 Set github
1.2 Flowchart
1.3 Database Construct
1.3.1 PostgreSql
2 | 2. Implementation |  |  |  |  | Frontend Delay
2.1 List of Branches
2.1.1 List of Data
2.1.2 Search functions
2.2 Set On-Demand
2.2.1 List of Data
2.2.2 Add
2.2.3 Edit
2.2.4 Removed
| 2.3 ReactJs |  |  |  |  | React Issues
2.3.1 React Components
2.3.2 home page
2.3.3 branch page
2.3.3.1 branch js implemetation
2.3.4 on demand page
2.3.4.1 on demand implementation
3 | 3. Testing Unit | [5 empty] | Frontend Delay
3.1 Brute Test
3.1.1 Backend (nodejs0
3.1.2 Frontend (Reactjs)
| 3.2 Injection Test | [5 empty] | Frontend Delay
3.2.1 Backend (nodejs0
3.2.2 Frontend (Reactjs)
4 | 4. Deployment | [5 empty] | Deployment Issues
4.1 Set postgresSql
4.2 Set nodejs
4.3 Set ReactJs
4.4 Beta Testing
4.4.1 Brute Test
4.4.2 Injection Test

## API
| [Domain] | http://localhost:3000/api
GROUP | METHOD | REQUIRED LOGIN | Extra Information (description) | URL | PARAMS |  | RESPONSE |  |  | STATUS | COMMENT
[5 empty] | NAME | Description | FORMAT | SUCCESS | ERROR/FAIL
Anonymous
Anonymous | GET | FALSE |  | [DOMAIN]/branches |  |  | status (bool) code (int) msg (str) data (object) | { status: true, code: 0, msg: "success", data: [ { id: 1, data: "values" } ] } | { status: true, code: 100, msg: "RecordNotFound" }
| POST | FALSE | form-data-urlencoded | [DOMAIN]/branches/list | id (int) |  | status (bool) code (int) msg (str) data (object) | { status: true, code: 0, msg: "success", data: [ { id: 1, data: "values" } ] } | { status: true, code: 100, msg: "RecordNotFound" }
| POST | FALSE | form-data-urlencoded | [DOMAIN]/branches | id (int) name (str) lat (str) log (str) price (float) day (int) start_time (int) end_time (int) | search by: - branch name OR meal package name - distance: latitude and longitude - price: less than equal - date and time: day and time | status (bool) code (int) msg (str) data (object) | { status: true, code: 0, msg: "success", data: [ { id: 1, data: "values" } ] } | { status: true, code: 100, msg: "RecordNotFound" }
| GET | FALSE |  | [DOMAIN]/onDemand |  |  | status (bool) code (int) msg (str) data (object) | { status: true, code: 0, msg: "success", data: [ { id: 1, data: "values" } ] } | { status: true, code: 100, msg: "RecordNotFound" }
| POST | FALSE | form-data-urlencoded | [DOMAIN]/onDemand | id (int) | find on-demand by id | status (bool) code (int) msg (str) data (object) | { status: true, code: 0, msg: "success", data: [ { id: 1, data: "values" } ] } | { status: true, code: 100, msg: "RecordNotFound" }
| POST | FALSE | form-data-urlencoded | [DOMAIN]/onDemand/add | bid (int) capacity (int) price (float) day (int) start_time (int) end_time (int) | add new on-demand | status (bool) code (int) msg (str) | { status: true, code: 0, msg: "success", data: [ { id: 1, data: "values" } ] } | { status: true, code: 100, msg: "RecordNotFound" }
| POST | FALSE | form-data-urlencoded | [DOMAIN]/onDemand/edit | id (int) bid (int) capacity (int) price (float) day (int) start_time (int) end_time (int) | edit on-demand by id | status (bool) code (int) msg (str) | { status: true, code: 0, msg: "success", data: [ { id: 1, data: "values" } ] } | { status: true, code: 100, msg: "RecordNotFound" }
| POST | FALSE | form-data-urlencoded | [DOMAIN]/onDemand/remove | id (int) | remove on-demand by id | status (bool) code (int) msg (str) | { status: true, code: 0, msg: "success", data: [ { id: 1, data: "values" } ] } | { status: true, code: 100, msg: "RecordNotFound" }

## Error Code
BASIC ERROR |  | API |  | FUNCTIONS
Code | Descriptions | Code | Descriptions | Code | Descriptions
1 | Invalid parameters | 100 | branch branchList() record not found | 1000 | branch branchList() error
|  | 101 | branch getAll() record not found | 1001 | branch getAll() error
|  | 102 | branch findById() record not found | 1002 | branch findById() error
|  | 103 | branch searchFilter() record not found | 1003 | branch searchFilter() error
|  | 104 | onDemand getAll() record not found | 1004 | onDemand getAll() error
|  | 105 | onDemand findById() record not found | 1005 | onDemand findById() error
|  | 106 | onDemand insertOne() unable to insert | 1006 | onDemand insertOne() error
|  | 107 | onDemand updated() record update not found | 1007 | onDemand updated() error
|  | 108 | onDemand removed() record delete not found | 1008 | onDemand removed() error